## Migration Checklist
Migration Checklist for project: template
No | Item | Forecast Hours | Actual time | Completion Date | Assigned Application Specialist | Remarks | Done
Migration planning and assessment
| Schedule Local Application Specialist training if required |  |  |  | Jordan | Migration webinars to be provided by global team, contact Jordan Dougherty to schedule.
| Identify Triggers that are actually being used, do not migrate triggers that are not enabled Master Folder For Triggers: \\rgppfil002.fdnet.com\shared$\F00CPA001\TRG_4April2016 |  |  |  | Local | We should only be migrating functionality that will be used. Disable or delete unused triggers | See list of Converted Triggers sheer
| Identify Reports that are actually being used Master Folder For Reports: \\rgppfil002.fdnet.com\shared$\F00CPA001\Reports |  |  |  | Local | Review list of reports with the project team and determine which should be migrated.
| Identify Views, Functions and Procedures |  |  |  | Local |  | only views PO and PO1, no functions or procedures
| Identify Link and email template (investigate a way to insert long names in the field) |  |  |  | Global and Local | Activity list link and supplier link
| Project reports and CFG files must be copied to the Citrix server R drive (identify where all reports are). This is especially important if the office or project uses ProArc Thick client. Make sure that the proper versions are places on the Citrix server. The Migration team will reference the Citrix server for the migration work. |  |  |  | Local |  | No thick client used | Reports are standard and run from \\rgppfil002\shared\Haarlem\Reports\GT640
| Run migration reports, and prework utilities - a tool that will extract the list of report from a source directory - extract list of triggers |  |  | 2016-08-02 | Sherwin | Global team will run this in all projects.
| Provide a migration overview to the project management team, and establish a high level migration schedule. Develop a communication plan to notify all users, internal and external. Schedule: Prework Stage 1 copy Notify project of upcoming migration User training Final Cutover |  |  |  | Local | Training materials available from Global Team
| Assign migration activities to specific individuals or groups. Identify who is responsible for the migration process the specific project and who is responsible in completing this checklist. Identify where this document should be posted |  |  |  | Who will do this? | Fill out this form [Who is responsible for updating this check list] The checklist will be uploaded in citrix R drive
| Update Project Database - schedule dates and work assignments |  |  |  | Jordan
Migration planning and assessment
| Run migration reports, and prework utilities (Migration Assesment) - a tool that will extract the list of report from a source directory - extract list of triggers Identify Views, Functions and Procedures Prepare migration checklist | 2 Hours |  | PAS - Config | Sherwin
| Migration Kick-Off Schedule prework assesment - meeting with Local applicaion specialsits Migration orientation and training if required Review migration data, establish preliminary migraiton schedule |  |  |  | Jordan | Migration webinars to be provided by global team, contact Jordan Dougherty to schedule.
| Confirm the Triggers that are actually being used, do not migrate triggers that are not enabled Identify triggers that are modified from the standard Master Folder For Triggers: \\rgppfil002.fdnet.com\shared$\F00CPA001\TRG_4April2016 |  | 2016-05-30 | 2016-06-01 | Local | We should only be migrating functionality that will be used. Disable or delete unused triggers
| Identify Reports that are actually being used Identify reprots that have been modifed from the standard Master Folder For Reports: \\rgppfil002.fdnet.com\shared$\F00CPA001\Reports |  | 2016-05-30 | 2016-06-04 | Local | Review list of reports with the project team and determine which should be migrated.
| Confirm and/or identify Views, Functions, and Procedures |  | 2016-05-30 | 2016-06-04 | Local
| Identify Link and email template (investigate a way to insert long names in the field) |  | 2016-06-04 | 2016-06-04 | Local | Activity list link and supplier link
| Project reports and CFG files must be copied to the Citrix server R drive (identify where all reports are). This is especially important if the office or project uses ProArc Thick client. Make sure that the proper versions are places on the Citrix server. The Migration team will reference the Citrix server for the migration work. |  | 2016-06-02 | 2016-06-02 | Local
| Provide a migration overview to the project management team, and establish a high level migration schedule. Develop a communication plan to notify all users, internal and external. Schedule: Prework Stage 1 copy Notify project of upcoming migration User training Final Cutover |  | 2016-06-01 | 2016-06-07 | Local | Training materials available from Global Team
| Review PCS Folder structure and Access control Identify any customized access control and determine how it will be supported after migration Delete unnecessary files and folders Use inherit access control where possible |  | 2016-06-04 | 2016-06-06 | Local | To verify this step - Global App Spec (Sherwin)
| Identify who will be configuring the project and who will be doing testing in 6.7. |  |  |  | Local | Lourdes Rubalcava - Configuring and Testing Oscar Lima - Testing Alma Gutierrez - Testing PDDM
| Assign migration activities to specific individuals or groups. Identify who is responsible for the migration process the specific project and who is responsible in completing this checklist. Identify where this document should be posted |  |  |  | Lourdes Rubalcava | Fill out this form [Who is responsible for updating this check list] The checklist will be uploaded in citrix R drive
| Update Project Database - schedule dates and work assignments |  |  |  | Jordan
| Determine if Native Archive is being used |  |  |  | Local
Prework Checklist - Database
| Convert the identified triggers to be migrated | 27 hours total 1 hour:1 trigger |  | PAS - Conversion | Global | Depends of how complex the trigger that will be converted. Compare project triggers to the triggers that have already been converted. Update triggers as required. Should have knowledge of SQL syntax
| Look for lines that have SQL syntax, convert from Oracle to SQL |  |  | PAS - Conversion | Global | Sherwin has a document with the most frequent cases (Common Syntax sheet and SQL Reference sheet)
| Copy the converted triggers to the folder (Triggers) in the migrated project folder in citrix R drive for later use |  |  | PAS - Conversion | Global
| Convert the identified reports to be migrated | 1 hour:1 report |  | PAS - Conversion | Global | Depends of how complex the report that will be converted
| Convert Views, Functions and Procedures |  |  | PAS - Conversion | Global
| Look for lines that have SQL syntax, convert from Oracle to SQL |  |  | PAS - Conversion | Global | Sherwin has a document with the most frequent cases (Common Syntax sheet and SQL Reference sheet)
| Copy the converted reports to the folder (Reports) in the migrated project folder in citrix R drive for later use |  |  | PAS - Conversion | Global
| Prepare a script to update of Initialization Rules, , External Validation, Result List, Workflow and Report List Table [Include Views, Functions and Procedures] |  |  | PAS - Conversion | Global
| Extract the following table information using the query below: - Initialization Rule select di_action from <Enter SchemaName>.DA_INIT; - External Validation select ut_name, ut_codefld, ut_descfld, ut_where from <Enter SchemaName>.DA_TYPE where ut_name is not null; - Result List select ls_exp from <Enter SchemaName>.LS_LISTSETUP; - Workflow select ss_sql from <Enter SchemaName>.SQL_SCRIPT; - Report List select rep_report, rep_filename from <Enter SchemaName>.REP_REPORT; | 15 minutes |  | PAS - Conversion
| Some standard changes and be scripted (search and replace). |  |  | PAS - Conversion | Global | We need to identify all the scripts that we want global admins to run
| Prepare a script that will convert the Initialization Rules table | 2 - 3 hours |  | PAS - Conversion | Global or Local | Review each item, identify changes to be made, then add to script, for unique SQL syntax. Define standard scripts for offices, where they have implemented the same configuration on many projects.
| Prepare a script that will convert the External Validation table | 1 - 2 hours |  | PAS - Conversion | Global or Local
| Prepare a script that will convert the Result List table | 15 minutes |  | PAS - Conversion | Global or Local
| Prepare a script that will convert the Workflow table | 1 - 2 hours |  | PAS - Conversion | Global or Local
| Prepare a script that will convert the Report List table | 15 minutes |  | PAS - Conversion | Global or Local
| Prepare a script that will update the sequence Table. Use the script below: update sequences set sq_count = (select max(change_event_rno) from changeevent) where sq_name = 'CHANGE_RNO' |  |  | PAS - Conversion | Global
| If Native archive is not being used, disable Native Trigger, Disable Native Archive |  |  | PAS - Conversion | Local
Prework Checklist - DMS and PCS
| Do a PCS/DMS/DMSWEB Pretest in 622 Verify the status of all functionality Test all reports, and document that they all run Test all archives | 1 hour |  | PAS-Tester | Global and Local | Verify that the functionality is working before we start the migration process, it is difficult to troubleshoot issues during or after the migration. [Need to trim test scripts so they can be completed in 2 hours] | done 05-30 2016
| Send a SRW to request normal project access to the original project using test accounts | 1 hour |  | PAS - Config or PAS - Tester | Global | Optional | done 05-30 2016
| add configuration participants to the XXXXXX_Project_Admin role of the original project |  |  | PAS - Config or PAS - Tester | Global |  | done 05-30 2016
| Send a SOR to add the test participants to the RTP_POLAdmin_CTX_ProArc2 group |  |  | PAS - Config or PAS - Tester | Global
| Verify that the information are updated in the R drive Ask the local POL Support to give a copy of the PROSETUP.INI, proarc4.cfg and customized reports if the project is using ProArc Thick client |  |  | PAS - Config or PAS - Tester | Global
| Prework is complete. Notify the migration coordinator that the prework is complete |  |  |  | Global
| Schedule Stage 1 Migration - coordinate with migration team, local application specialists and project team. |  |  |  | Migration Coordinator
| Submit requests for Stage 1 Migration |  |  |  | Global
* | Run ERR Audit Report - send it to the local office and project team for action |  |  |  | Global |  | done 05-26 2016
Stage 1 Migration Checklist
| Freeze on configuration changes - Notify Project Team |  |  |  | Local
| Request CWX 6.7 Citrix folders |  |  |  | POL Services
| Copy DMS database and upgrade to Coreworx 6.7 |  |  |  | Global Administrator
| Copy PCS folder structure to Coreworx 6.7 run script to set access rights for XXXXXXX_Project_Admin |  |  |  | Global Administrator
| Update Views |  |  |  | Global Admin
Stage 1 Migration Checklist - Database
|  | 1-2 hours |  | PAS - Config
| Connect to MSSQL project database server using SQL Server Management Studio |  |  | PAS - Config | Global
| Validate if the views are properly imported |  |  | PAS - Config | Global App Spec
| Execute the script that will add the converted triggers to the migrated project database |  |  | PAS - Config | Global
| Execute the script that will update the Initialization Rules, External Validation, Result List, Workflow and Report List are properly converted |  |  | PAS - Config | Global
| Execute the script that will update sequence Table |  |  | PAS - Config | Global
Stage 1 Migration Checklist - DMS and PCS
| Copy PROSETUP.INI from the original project to the migrated project on the Citrix share drive | 1 hours |  | PAS - Config | Global
| Open Prosetup and go to the Misc Section | (7-8 total) |  | PAS - Config | Global
| Select File then Import Config Files, click OK |  |  | PAS - Config | Global
| The imported entries will be displayed in Red |  |  | PAS - Config | Global
| Click File then select Import to Database |  |  | PAS - Config | Global
| On the Duplicate Keys option, select "Always overwrite with INI-file settings |  |  | PAS - Config | Global
| In ProSetup - Related Info, verify that all sql syntax for Initialization Rules, External Validation and Result List are correct |  |  | PAS - Config | Global
| In Proflow - Related Info, verify that all sql syntax for Workflow Scripts are correct |  |  | PAS - Config | Global
| Register each converted report | 1 - 2 hours |  | PAS - Config or PAS - Tester | Global
| DMS Testing and remove test data | 4 hours |  | PAS-Tester | Global and Local
DMS for Stage 1 Complete
| Configure PCS Access rights on top level folders Administrator 03-Business Admin 01-Global Admin 02-User Admin XX_PROJECT_FLUOR_ADMIN |  |  |  | Global
| Add parent to xxxxxxxx_COMMON - XX_PROJECT_FLUOR_USERS |  |  |  | Global
| Provide ProArc access to the user who will do the PCS and PAWeb Testing by navigating the Coreworx menu: Administration - Users - Manage |  |  |  | Global
| PCS and PAWeb Testing | 1 - 2 hours |  |  | Global and Local
| Approval to proceed with migration |  |  |  | local
| Migration Scheduled |  |  |  | Migration Coordinator
| Submit requests for Final Migration |  |  |  | Global
| Provide migration training to project users - with in 2 weeks of migration |  |  |  | local | Training materials available from Global Team
| Send migration notification out to the project team |  |  |  | local | [Jordan to develop template]
| Update Project Database - schedule dates and work assignments |  |  |  | Jordan
Stage 2 - Final Cutover Migration Checklist
| Global Admin Activities | 4-6 hours
| Disable POL 6.2.2 project |  |  |  | Global Administrator
| Update files/blobs, run CPA to copy PCS folder structure |  |  |  | Global Administrator
| Grant ProArc Access for DMS users |  |  |  | Global Administrator
| Enable Citrix access for DMS users |  |  |  | Global Administrator
| Application Specialist Activities | Two people 3-4 hours total
| Import ProSetup configuration | 30 min Configuration work |  | PAS - Config
| Copy PROSETUP.INI from the original project to the migrated project on the Citrix share drive |  |  | PAS - Config | Global
| Open Prosetup and go to the Misc Section |  |  | PAS - Config | Global
| Select File then Import Config Files, click OK |  |  | PAS - Config | Global
| The imported entries will be displayed in Red |  |  | PAS - Config | Global
| Click File then select Import to Database |  |  | PAS - Config | Global
| On the Duplicate Keys option, select "Always overwrite with INI-file settings |  |  | PAS - Config | Global
| Verify ProArc/Proflow settings |  |  | PAS - Config
| In ProSetup - Related Info, verify that all sql syntax for Initialization Rules, External Validation and Result List are correct |  |  | PAS - Config | Global
| In Proflow - Related Info, verify that all sql syntax for Workflow Scripts are correct |  |  | PAS - Config | Global
| Verify that updated triggers, INIT rules are implemented |  |  | PAS - Config | Global
| Verify the updated views, Functions, Procedures are implemented |  |  | PAS - Config | Global
| DMS Testing | 2 hours DMS Testing |  | PAS-Tester Can be two testers | Global and Local
| Configure PCS Access rights on Project Folder Only Administrator -(enable all permissions) 03-Business Admin (Manage Permission-omit on behalf of, enable all other permissions) 01-Global Admin(enable all permissions) 02-User Admin(Manage Permission-omit on behalf of, enable all other permissions) XX_PROJECT_FLUOR_ADMIN(Manage Permission-omit on behalf of, enable all other permissions) | 1 hours PCS Configuration and Testing |  | PAS - Config or PAS - Tester | Global
| Add parent to xxxxxxxx_COMMON - XX_PROJECT_FLUOR_USERS |  |  |  | Global
| PCS and PAWeb Testing |  |  | PAS-Tester | Global and Local
| Remove/delete test data and document profile |  |  | PAS-Tester | Global and Local
| Approval to go live |  |  |  | local
| Update Project Database - schedule dates and work assignments |  |  |  | Jordan

## Statistics
Office | Mexico City
Project Number | F00007430
Project Name | Conversion de Residuales Salamanca
Primary Project Workhours | 13:00 UTC - 22:00 UTC
Stage 2 - Final Cutover Outage | 22:00 UTC - 13:00 UTC
Stage 1 Date |  |  | *Date must be confirmed with migration coordinator
Stage 2 - Final Cutover Date |  |  | *Date must be confirmed with migration coordinator
Item | Total Count |  | Custom Items | Notes | MC Comments
External Validation |  | 0 |  | rows will be converted to 6.7
Initialization Rules |  | 0 |  | rows will be converted to 6.7
Result List |  | 0 |  | rows will be converted to 6.7
Reports |  | 0 | count any non-standard reprorts | reports will be converted to 6.7
Triggers |  | 24 | Count the number of Triggers that are not standard | -24 triggers will be converted to 6.7
Views |  |  | Count any non-standard views
Stored Procedures |  |  | Count any non-standard procedures
Functions |  |  | Count any non standard funciton
Workflow |  | 0 | count any non standard wf | rows will be converted to 6.7
Archive | Count Document
EDR
ENGRDOCS
PROJEXEC
TRANS
| Prework (hrs.) |  | Stage 1 - Data Copy (hrs.) | Stage 2 - Final Cutover (hrs.) | Total App Specialist Hours (hrs.)
Standard | Calculation of hours for a standard proejct |  | Calculation of hours for a standard proejct | Calculation of hours for a standard proejct | 0
Custom | Calculation of hours for the customized items |  | Calculation of hours for the customized items | Calculation of hours for the customized items | 0
|  |  |  | Grand Total | 0

## Reports
Project Name | List of Registered POL 6.2.2 Reports Reports Path: \\rgppfil002.fdnet.com\shared$\00007430\Reports | Office to Confirm that this reprot is being used by the proejct and should be migrated ( In use/Do not migrate) | Report converted | Location of converted reprots on Citrix server (new subfolder)
Reports From \\rgppfil002.fdnet.com\shared$\00007430\671\Reports

## Triggers
Trigger | Scrip

## Views
FTF_FILETYPE_FILTER
IMAGE_FILES_SEC
PO
PO1
REC_ADDRESS
SI_COLUMNS
SI_TABLES
ENGRDOCS
CPY
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status Date | Status Date | 12 | Date | STATDATE - DOCUMENT
| 2. Attribute, multiple | Planta | Planta | 15 | Char | CA_WBSUNIT - DA
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Response Due Date | Response Due Date | 12 | Date | RESDUE - DX_2
| 1. Attribute, single | Received Date Commen | Received Date Commen | 12 | Date | REC_DAT - DX_2
| 1. Attribute, single | TXML Comment | TXML Comment | 100 | Char | TXML_COM - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 35 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 3. Sub Select | Received Pemex Date | Received Pemex Date | 12 | Date | select REC_PEMEX from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Numero Anterior | Numero Anterior | 30 | Char | NUM_ANT - DX_2
| 1. Attribute, single |  | Responsible Office* | 10 | Char | RESPOFFICE - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single |  | Desc Document Type | 100 | Char | DOCTYPE_D - DX_2
ENG LIST FULL
| 1. Attribute, single | Document Number | Document Number | 20 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Document Title | Document Title | 25 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Transmittal Number | Transmittal Number | 25 | Char | TRANSNO - DX_2
ENG LIST SIMPLE
| 1. Attribute, single | Document Number | Document Number | 20 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Document Title | Document Title | 25 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Transmittal Number | Transmittal Number | 25 | Char | TRANSNO - DX_2
ENGR DOC LIST
| 1. Attribute, single |  | Responsible Office* | 10 | Char | RESPOFFICE - DX_2
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 2. Attribute, multiple | WBS Unit | WBS Unit | 15 | Char | CA_WBSUNIT - DA
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Transmittal Number | Transmittal Number | 25 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 3. Sub Select |  | Proarc File Name | 20 | Char | select fi_filename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 3. Sub Select |  | Orig File Name | 20 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 1. Attribute, single |  | ISO Destination | 30 | Char | ISO_DESTINATION - DX_2
| 2. Attribute, multiple | Sub-Contract No. | Sub-Contract No. | 90 | Char | CA_SUBCONT - DA
| 1. Attribute, single | IFD Plan | IFD Plan | 12 | Date | IFD_PLAN - DX_2
| 1. Attribute, single | IFD Forecast | IFD Forecast | 12 | Date | IFD_FCST - DX_2
| 1. Attribute, single | IFC Plan | IFC Plan | 12 | Date | IFC_PLAN - DX_2
| 1. Attribute, single | IFC Forecast | IFC Forecast | 12 | Date | IFC_FCST - DX_2
| 3. Sub Select | type |  | 10 | Char | select fi_type from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
FILES
| 1. Attribute, single | Document Number | Document Number | 30 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Document Title | Document Title | 50 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 25 | Char | REVISION - DOCUMENT
| 3. Sub Select |  | FilenameLastRev | 30 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 1. Attribute, single | Status | Status | 25 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Discipline | Discipline | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 50 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 2. Attribute, multiple | Equip Tag ID | Equip Tag ID | 90 | Char | CA_EQUIPTG - DA
| 2. Attribute, multiple | WBS Area | WBS Area | 25 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | WBS Unit | WBS Unit | 25 | Char | CA_WBSUNIT - DA
| 2. Attribute, multiple | WBS System | WBS System | 25 | Char | CA_WBSSYS - DA
| 1. Attribute, single | Comments | Comments | 50 | Char | COMMENTS - DX_2
| 1. Attribute, single |  | Responsible Office* | 10 | Char | RESPOFFICE - DX_2
IDCT
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Etapa | Etapa | 15 | Char | CA_PHASE - DX_2
| 2. Attribute, multiple | Planta | Planta | 15 | Char | CA_WBSUNIT - DA
| 2. Attribute, multiple | Area Seccion | Area Seccion | 15 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | Fase | Fase | 15 | Char | CA_WBSSYS - DA
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single | Desc Tipo Doc. | Desc Tipo Doc. | 100 | Char | DOCTYPE_D - DX_2
| 1. Attribute, single | Formato | Formato | 15 | Char | DRAWSIZE - DX_2
| 1. Attribute, single | Sheet No | Sheet No | 3 | Char | ED_SHTNO - DX_2
| 2. Attribute, multiple | Equip. Tag | Equip. Tag | 90 | Char | CA_EQUIPTG - DA
| 1. Attribute, single | Actividad de la Red | Actividad de la Red | 25 | Char | ACT_RED - DX_2
| 1. Attribute, single | Descripción de la Ac | Descripción de la Ac | 25 | Char | DESC_ACT - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 25 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
IMPOR_ENGRDOCS
| 1. Attribute, single | Project No | Project No | 50 | Char | CA_CONTRNO - DX_2
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Etapa | Etapa | 15 | Char | CA_PHASE - DX_2
| 2. Attribute, multiple | Planta | Planta | 15 | Char | CA_WBSUNIT - DA
| 2. Attribute, multiple | Area Seccion | Area Seccion | 15 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | Fase | Fase | 15 | Char | CA_WBSSYS - DA
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single |  | Descripcion Doc type | 100 | Char | DOCTYPE_D - DX_2
| 1. Attribute, single | Formato | Formato | 15 | Char | DRAWSIZE - DX_2
| 1. Attribute, single | Sheet No | Sheet No | 3 | Char | ED_SHTNO - DX_2
| 1. Attribute, single | Actividad de la Red | Actividad de la Red | 25 | Char | ACT_RED - DX_2
| 1. Attribute, single | Descripción de la Ac | Descripción de la Ac | 100 | Char | DESC_ACT - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 35 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 1. Attribute, single |  | Responsible Office* | 10 | Char | RESPOFFICE - DX_2
| 1. Attribute, single | SRD | SRD | 20 | Char | SRD - DX_2
| 2. Attribute, multiple | Equip. Tag | Equip. Tag | 90 | Char | CA_EQUIPTG - DA
| 1. Attribute, single |  | Responsible Engineer | 25 | Char | ORIGENG - DX_2
| 1. Attribute, single | Response Due Date | Response Due Date | 12 | Date | RESDUE - DX_2
| 3. Sub Select | rev date | rev date | 12 | Char | select initiated from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| 3. Sub Select |  | File | 100 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 3. Sub Select |  | File | 100 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 3. Sub Select |  | File | 100 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 3. Sub Select |  | File | 100 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
MAIN ATTRIBUTES
| 1. Attribute, single | Document Number | Document Number | 30 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Document Title | Document Title | 50 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 25 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 25 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Discipline | Discipline | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 50 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 2. Attribute, multiple | Equip Tag ID | Equip Tag ID | 90 | Char | CA_EQUIPTG - DA
| 2. Attribute, multiple | Sub-Project Name | Sub-Project Name | 50 | Char | CA_SPRNAME - DA
| 2. Attribute, multiple | WBS Area | WBS Area | 25 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | WBS Unit | WBS Unit | 25 | Char | CA_WBSUNIT - DA
| 2. Attribute, multiple | WBS System | WBS System | 25 | Char | CA_WBSSYS - DA
| 1. Attribute, single | Comments | Comments | 50 | Char | COMMENTS - DX_2
| 2. Attribute, multiple | Sub-Contract No | Sub-Contract No | 90 | Char | CA_SUBCONT - DA
MDR
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 35 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 2. Attribute, multiple | Equip. Tag | Equip. Tag | 90 | Char | CA_EQUIPTG - DA
| 2. Attribute, multiple | Sub-Project Name | Sub-Project Name | 50 | Char | CA_SPRNAME - DA
| 2. Attribute, multiple | Area Seccion | Area Seccion | 15 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | Planta | Planta | 15 | Char | CA_WBSUNIT - DA
| 2. Attribute, multiple | Fase | Fase | 15 | Char | CA_WBSSYS - DA
| 1. Attribute, single | Comments | Comments | 255 | Char | COMMENTS - DX_2
| 1. Attribute, single |  | Responsible Office* | 10 | Char | RESPOFFICE - DX_2
| 2. Attribute, multiple | Sub-Contract No. | Sub-Contract No. | 90 | Char | CA_SUBCONT - DA
RESULT LIST
| 1. Attribute, single | As-Built Required | As-Built Required | 3 | Char | ASBUILT - DX_2
| 1. Attribute, single |  | CAD File Name | 50 | Char | CAD_FILE_NAME - DX_2
| 1. Attribute, single | Project No | Project No | 50 | Char | CA_CONTRNO - DX_2
| 1. Attribute, single | Project Name | Project Name | 50 | Char | CA_PRONAME - DX_2
| 1. Attribute, single | System Description | System Description | 50 | Char | CA_SYSDESC - DX_2
| 1. Attribute, single |  | Client Native Filena | 50 | Char | CLIENT_NATIVEFILENAM - DX_2
| 1. Attribute, single |  | RTN Trans. No. | 30 | Char | CLIENT_RTN_TXML_NO - DX_2
| 1. Attribute, single |  | Client Trans. No. | 30 | Char | CLIENT_TXML_NO - DX_2
| 1. Attribute, single | Client Document Numb | Client Number | 20 | Char | CLNT_DOCNO - DX_2
| 1. Attribute, single | Comments | Comments | 255 | Char | COMMENTS - DX_2
| 1. Attribute, single | Created Date | Created Date | 12 | Date | CREATED - DOCUMENT
| 1. Attribute, single | Created By | Created By | 10 | Char | CREATED_BY - DOCUMENT
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single |  | Drawing Size | 8 | Char | DRAWSIZE - DX_2
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single | IFA Actual | IFA Actual | 12 | Date | IFA_ACTUAL - DX_2
| 1. Attribute, single | IFA Forecast | IFA Forecast | 12 | Date | IFA_FCST - DX_2
| 1. Attribute, single | IFA Plan | IFA Plan | 12 | Date | IFA_PLAN - DX_2
| 1. Attribute, single | IFC Actual | IFC Actual | 12 | Date | IFC_ACTUAL - DX_2
| 1. Attribute, single | IFC Forecast | IFC Forecast | 12 | Date | IFC_FCST - DX_2
| 1. Attribute, single | IFC Plan | IFC Plan | 12 | Date | IFC_PLAN - DX_2
| 1. Attribute, single | IFD Actual | IFD Actual | 12 | Date | IFD_ACTUAL - DX_2
| 1. Attribute, single | IFD Forecast | IFD Forecast | 12 | Date | IFD_FCST - DX_2
| 1. Attribute, single | IFD Plan | IFD Plan | 12 | Date | IFD_PLAN - DX_2
| 1. Attribute, single | IFR Actual | IFR Actual | 12 | Date | IFR_ACTUAL - DX_2
| 1. Attribute, single | IFR Forecast | IFR Forecast | 12 | Date | IFR_FCST - DX_2
| 1. Attribute, single | IFR Plan | IFR Plan | 12 | Date | IFR_PLAN - DX_2
| 1. Attribute, single |  | ISO Destination | 30 | Char | ISO_DESTINATION - DX_2
| 1. Attribute, single |  | ISO Fab Category | 10 | Char | ISO_FAB_CATEGORY - DX_2
| 1. Attribute, single |  | ISO Commodity | 30 | Char | ISO_FLUID - DX_2
| 1. Attribute, single |  | ISO Line No. | 30 | Char | ISO_LINE_NO - DX_2
| 1. Attribute, single |  | ISO Priority | 30 | Char | ISO_PRIORITY - DX_2
| 1. Attribute, single |  | ISO Piping Trans No. | 30 | Char | ISO_TRANS_NO - DX_2
| 1. Attribute, single | Modified By | Modified By | 20 | Char | MODIFIED_BY - DOCUMENT
| 1. Attribute, single | Modified Date | Modified Date | 12 | Date | MODIFIED_M - DOCUMENT
| 1. Attribute, single |  | Responsible Engineer | 25 | Char | ORIGENG - DX_2
| 1. Attribute, single |  | Original Received | 12 | Date | ORIGRECD - DX_2
| 1. Attribute, single |  | Original Requestor | 25 | Char | ORIGREQUEST - DX_2
| 1. Attribute, single |  | Original Returned | 12 | Date | ORIGRTND - DX_2
| 1. Attribute, single | Plant Original | Plant Original | 3 | Char | PLANTORIG - DX_2
| 1. Attribute, single | Response Due Date | Response Due Date | 12 | Date | RESDUE - DX_2
| 1. Attribute, single | Response Expected | Response Expected | 3 | Char | RESEXP - DX_2
| 1. Attribute, single |  | Responsible Office* | 10 | Char | RESPOFFICE - DX_2
| 1. Attribute, single |  | Response Received | 12 | Date | RESREC - DX_2
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single |  | Schedule Reference I | 15 | Char | SCH_REFID - DX_2
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | SubContractor Trans | SubContractor Trans | 12 | Date | SUB_TRANSDATE - DX_2
| 1. Attribute, single | SubContractor Trans | SubContractor Trans | 25 | Char | SUB_TRANSNO - DX_2
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 1. Attribute, single | Transmittal Number | Transmittal Number | 25 | Char | TRANSNO - DX_2
| 2. Attribute, multiple | Equip. Tag | Equip. Tag | 90 | Char | CA_EQUIPTG - DA
| 2. Attribute, multiple | Sub-Project Name | Sub-Project Name | 50 | Char | CA_SPRNAME - DA
| 2. Attribute, multiple | Sub-Contract No. | Sub-Contract No. | 90 | Char | CA_SUBCONT - DA
| 2. Attribute, multiple | System Turnover No | System Turnover No | 15 | Char | CA_SYSTURN - DA
| 2. Attribute, multiple | Transmittal Log | Transmittal Log | 50 | Char | CA_TRANSMITTAL - DA
| 2. Attribute, multiple | WBS Area | WBS Area | 15 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | WBS System | WBS System | 15 | Char | CA_WBSSYS - DA
| 2. Attribute, multiple | WBS Unit | WBS Unit | 15 | Char | CA_WBSUNIT - DA
| 2. Attribute, multiple | Construction Work Pk | Constr. Work Pkg. | 15 | Char | CA_WORKPKG - DA
| 3. Sub Select |  | OrigFilenameRevLvl | 20 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 3. Sub Select |  | OrigFilenameDocLvl | 20 | Char | select fi_orgfilename from {schema} fi_file F, {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno}
STANDARD
| 1. Attribute, single | Document No. | Document No.* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
TLMD
| 1. Attribute, single | Document No* | Document No* | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Title | Document Title* | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Project Name | Project Name | 50 | Char | CA_PRONAME - DX_2
| 1. Attribute, single | Etapa | Etapa | 15 | Char | CA_PHASE - DX_2
| 2. Attribute, multiple | Area Seccion | Area Seccion | 15 | Char | CA_WBSAREA - DA
| 2. Attribute, multiple | Fase | Fase | 15 | Char | CA_WBSSYS - DA
| 1. Attribute, single | Discipline | Discipline* | 50 | Char | ED_DOCCAT - DX_2
| 1. Attribute, single | Document Type | Document Type* | 50 | Char | ED_DOCTYPE - DX_2
| 1. Attribute, single | Formato | Formato | 8 | Char | DRAWSIZE - DX_2
| 1. Attribute, single | Sheet No | Sheet No | 3 | Char | ED_SHTNO - DX_2
| 2. Attribute, multiple | Equip. Tag | Equip. Tag | 90 | Char | CA_EQUIPTG - DA
| 1. Attribute, single | Transmittal Number | Transmittal Number | 25 | Char | TRANSNO - DX_2
| 1. Attribute, single | Transmittal Date | Transmittal Date | 12 | Date | TRANSDATE - DX_2
| 1. Attribute, single | Project No | Project No | 50 | Char | CA_CONTRNO - DX_2
| 1. Attribute, single | Comments | Comments | 255 | Char | COMMENTS - DX_2
PROJEXEC
BITACORA
| 1. Attribute, single | Document Number | Document Number | 50 | Char | DOC_ID - DOCUMENT
| 3. Sub Select | Fecha Ing PDDM | Fecha Ing PDDM | 20 | Char | select initiated from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| 1. Attribute, single | Documentos Afectados | Documentos Afectados | 255 | Char | DOC_AFEC - DX_12
| 1. Attribute, single | Clasificacion del Ca | Clasificacion del Ca | 25 | Char | CA_NCD - DX_12
| 1. Attribute, single | Title | Title | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | P-42 | P-42 | 3 | Char | CA_NOYES - DX_12
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 3. Sub Select | Respuesta | Respuesta | 12 | Date | select STATDATE from {schema}REVISION where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
PROJEXEC
| 1. Attribute, single | Doc.no | Doc.no | 60 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Title | Title | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Document Category | Document Category | 20 | Char | PE_DOCCAT - DX_12
| 1. Attribute, single | Document Type | Document Type | 50 | Char | PE_DOCTYPE - DX_12
| 1. Attribute, single | Issued Date | Issued Date | 12 | Char | CA_ISSDATE - DX_12
| 1. Attribute, single | Author | Author | 50 | Char | PE_AUTHOR - DX_12
ALL_ATTRIBUTES
| 1. Attribute, single | Comments | Comments | 255 | Char | CA_COMMNTS - DX_12
| 1. Attribute, single | Project No | Project No | 50 | Char | CA_CONTRNO - DX_12
| 1. Attribute, single | Issued Date | Issued Date | 12 | Date | CA_ISSDATE - DX_12
| 1. Attribute, single | Project Name | Project Name | 50 | Char | CA_PRONAME - DX_12
| 1. Attribute, single | Security Classificat | Security Classificat | 30 | Char | CA_SECURCL - DX_12
| 1. Attribute, single | Client | Client | 12 | Char | CLIENT - DX_12
| 1. Attribute, single | Company | Company | 20 | Char | COMPANY - DX_12
| 1. Attribute, single | To Company | To Company | 20 | Char | COMPANY_TO - DX_12
| 1. Attribute, single | Created Date | Created Date | 12 | Date | CREATED - DOCUMENT
| 1. Attribute, single | Created By | Created By | 10 | Char | CREATED_BY - DOCUMENT
| 1. Attribute, single | Discipline | Discipline | 20 | Char | DISCIP - DX_12
| 1. Attribute, single | Document Number | Document Number | 50 | Char | DOC_ID - DOCUMENT
| 1. Attribute, single | Document status | Document status | 25 | Char | D_STATUS - DX_12
| 1. Attribute, single | Format | Format | 10 | Char | FORMAT_ID - DOCUMENT
| 1. Attribute, single | Modified By | Modified By | 20 | Char | MODIFIED_BY - DOCUMENT
| 1. Attribute, single | Modified Date | Modified Date | 12 | Date | MODIFIED_M - DOCUMENT
| 1. Attribute, single | Paper Copy | Paper Copy | 3 | Char | PAPER - DX_12
| 1. Attribute, single | Document Type | Document Type | 50 | Char | PE_DOCTYPE - DX_12
| 1. Attribute, single | Response Expected | Response Expected | 10 | Char | RES_EXP - DX_12
| 1. Attribute, single | Response Received | Response Received | 50 | Char | RES_REC - DX_12
| 1. Attribute, single | Return Date | Return Date | 12 | Date | RET_DATE - DX_12
| 1. Attribute, single | Revision | Revision | 20 | Char | REVISION - DOCUMENT
| 1. Attribute, single | Original Signed By | Original Signed By | 20 | Char | SIGN - DX_12
| 1. Attribute, single | Status Date | Status Date | 12 | Date | STATDATE - DOCUMENT
| 1. Attribute, single | Status | Status | 20 | Char | STATUS - DOCUMENT
| 1. Attribute, single | Title | Title | 255 | Char | TITLE - DOCUMENT
| 1. Attribute, single | Version | Version | 10 | Char | VERSION - DOCUMENT
| 2. Attribute, multiple | Sub-Project Name | Sub-Project Name | 30 | Char | CA_SPRNAME - DA
| 3. Sub Select |  | OrigFilenameRevLvl | 20 | Char | select fi_orgfilename from {schema} fi_file F {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno} and r.rev_id = {rev_id}
| 3. Sub Select |  | OrigFilenameDocLvl | 20 | Char | select fi_orgfilename from {schema} fi_file F {schema}rf_rev_file R where F.fi_file_rno = R.fi_file_rno and R.doc_rno = {doc_rno}

## Stored Procedures
N/A

## Functions
N/A

## Initialisation Rules
ENGRDOCS
| <Form> | INSERT | CA_PRONAME | 1 | S:SELECT CA_PRONAME from {schema}CALOOKUP_CA_PRONAME
| <Form> | UPDATE | CA_PRONAME | 1 | S:SELECT CA_PRONAME from {schema}CALOOKUP_CA_PRONAME
| <Form> | LOAD | CA_PRONAME | 1 | S:SELECT CA_PRONAME from {schema}CALOOKUP_CA_PRONAME
| <Form> | INSERT | CA_CONTRNO | 1 | S:SELECT CA_CONTRNO from {schema}CALOOKUP_CA_CONTRNO
| <Form> | UPDATE | CA_CONTRNO | 1 | S:SELECT CA_CONTRNO from {schema}CALOOKUP_CA_CONTRNO
| <Form> | LOAD | CA_CONTRNO | 1 | S:SELECT CA_CONTRNO from {schema}CALOOKUP_CA_CONTRNO
| <Form> | UPDATE | DOC_ID | 1 | S:update {SCHEMA}document set doc_id = 'NATIVE-' ¦¦ '{doc_id}' where doc_rno = ( select doc_rno2 from {SCHEMA}docstruc where doc_rno = {doc_rno} and db_rno = 2 and db_rno2 = 11 )
| <Form> | UPDATE | ED_DOCCAT | 1 | S:update {SCHEMA}DX_11 set ED_DOCCAT = '{ED_DOCCAT}' where doc_rno = ( select doc_rno2 from {SCHEMA}docstruc where doc_rno = {doc_rno} and db_rno = 2 and db_rno2 = 11 )
| <Form> | UPDATE | ED_DOCTYPE | 1 | S:update {SCHEMA}DX_11 set ED_DOCTYPE = '{ED_DOCTYPE}' where doc_rno = ( select doc_rno2 from {SCHEMA}docstruc where doc_rno = {doc_rno} and db_rno = 2 and db_rno2 = 11 )
| <Form> | REVCHANGE | REVISION | 1 | S:DELETE FROM {SCHEMA}REVISION WHERE DOC_RNO = (SELECT DOC_RNO2 FROM {SCHEMA}DOCSTRUC WHERE DOC_RNO='{DOC_RNO}'AND DB_RNO={DB_RNO} AND DB_RNO2=11)
| <Form> | REVCHANGE | REVISION | 1 | S:INSERT INTO {SCHEMA}REVISION(REV_ID,VER_ID,DOC_RNO,DB_RNO,STATUS,STATUS_USERID,REVISION,REV_SEQNO,INITIATED,INITIATED_USERID,STATDATE) SELECT R.REV_ID, R.VER_ID, D.DOC_RNO2, D.DB_RNO2, R.STATUS, R.STATUS_USERID, R.REVISION, R.REV_SEQNO, R.INITIATED, R.INITIATED_USERID, R.STATDATE FROM {SCHEMA}REVISION R, {SCHEMA}DOCSTRUC D WHERE D.DOC_RNO={DOC_RNO} AND R.DOC_RNO=D.DOC_RNO AND D.DB_RNO=2 AND D.DB_RNO2=11
| <Form> | REVCHANGE | REVISION | 1 | S:UPDATE {SCHEMA}DOCUMENT SET REVISION=(SELECT REVISION FROM {SCHEMA}DOCUMENT WHERE DOC_RNO={DOC_RNO}), STATUS=(SELECT STATUS FROM {SCHEMA}DOCUMENT WHERE DOC_RNO={DOC_RNO}), REV_ID=(SELECT REV_ID FROM {SCHEMA}DOCUMENT WHERE DOC_RNO={DOC_RNO}), VER_ID=(SELECT VER_ID FROM {SCHEMA}DOCUMENT WHERE DOC_RNO={DOC_RNO}), STATDATE=(SELECT STATDATE FROM {SCHEMA}DOCUMENT WHERE DOC_RNO={DOC_RNO}) WHERE DOC_RNO=(SELECT DOC_RNO2 FROM {SCHEMA}DOCSTRUC WHERE DOC_RNO={DOC_RNO} AND DB_RNO=2 AND DB_RNO2=11)
| <Form> | SELECT | CA_SPRNAME | 1 | S:DELETE FROM {SCHEMA}DA WHERE DOC_RNO = ( SELECT DOC_RNO2 FROM {SCHEMA}DOCSTRUC WHERE DOC_RNO={DOC_RNO} AND DB_RNO={DB_RNO} AND DB_RNO2=11 ) AND NAME = 'CA_SPRNAME' AND DB_RNO = 11
| <Form> | SELECT | CA_SPRNAME | 1 | S:INSERT INTO {SCHEMA}DA ( DOC_RNO, DB_RNO, NAME, VALUE, DA_SORTORDER ) SELECT D.DOC_RNO2, 11, 'CA_SPRNAME', A.VALUE, A.DA_SORTORDER FROM {SCHEMA}DA A, {SCHEMA}DOCSTRUC D WHERE D.DOC_RNO={DOC_RNO} AND D.DB_RNO={DB_RNO} AND D.DB_RNO2=11 AND A.DOC_RNO = D.DOC_RNO AND A.NAME = 'CA_SPRNAME'
| <Form> | SELECT | REVSTAT | 1 | S:update {schema}dx_2 set revstat = ( select status from {schema}document where doc_rno = {doc_rno} ) where doc_rno = {doc_rno}
| <Form> | INSERT | PFI_DISC | 1 | V:206
| <Form> | INSERT | PFI_DISC_D | 1 | V:Project Document and Data Management
| <Form> | INSERT | PFI_FACILITY | 1 | S:SELECT PFI_FACILITY from {schema}CALOOKUP_PFI_FACILITY
| <Form> | INSERT | PFI_PROJCITY | 1 | S:SELECT PFI_PROJCITY from {schema}CALOOKUP_PFI_PROJCITY
| <Form> | INSERT | PFI_PROJCTRY | 1 | S:SELECT PFI_PROJCTRY from {schema}CALOOKUP_PFI_PROJCTRY
| <Form> | INSERT | PFI_PROJSTATE | 1 | S:SELECT PFI_PROJSTATE from {schema}CALOOKUP_PFI_PROJSTATE
| <Form> | INSERT | PFI_BUSLINE | 1 | S:SELECT PFI_BUSLINE from {schema}CALOOKUP_PFI_BUSLINE
| <Form> | INSERT | PFI_CLIENT | 1 | S:SELECT PFI_CLIENT from {schema}CALOOKUP_PFI_CLIENT
| <Form> | INSERT | PFI_COSTCENTER | 1 | S:SELECT PFI_COSTCENTER from {schema}CALOOKUP_PFI_COSTCENTER
| <Form> | INSERT | PFI_SBU | 1 | S:SELECT PFI_SBU from {schema}CALOOKUP_PFI_SBU
| <Form> | INSERT | PFI_CODE_D | 1 | S:select descript from {schema}ENGRDOCS_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| <Form> | SELECT | PFI_CODE_D | 1 | S:select descript from {schema}ENGRDOCS_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| <Form> | UPDATE | PFI_CODE_D | 1 | S:update {schema}dx_2 set PFI_CODE_D= ( select distinct descript from {schema}ENGRDOCS_PFI_CODE PF where PF.ED_DOCTYPE = '{ED_DOCTYPE}' ) where doc_rno = {doc_rno}
| <Form> | INSERT | PFI_POLICY | 1 | V:40
| <Form> | LOAD | PFI_CAT | 1 | V:206A
| <Form> | INSERT | PFI_CAT | 1 | V:206A
| <Form> | UPDATE | PFI_CAT | 1 | V:206A
| <Form> | LOAD | PFI_CAT_D | 1 | V:PDDM
| <Form> | INSERT | PFI_CAT_D | 1 | V:PDDM
| <Form> | UPDATE | PFI_CAT_D | 1 | V:PDDM
| <Form> | INSERT | PFI_CODE | 1 | S:select PFI_CODE from {schema}ENGRDOCS_PFI_CODE PF where PF.ED_DOCTYPE = '{ED_DOCTYPE}'
| <Form> | UPDATE | PFI_CODE | 1 | S:update {schema}dx_2 set PFI_CODE= (select distinct PFI_CODE from {schema}ENGRDOCS_PFI_CODE PF where PF.ED_DOCTYPE = '{ED_DOCTYPE}' ) where doc_rno = {doc_rno}
| ED_DOCTYPE | CHANGE | PFI_CODE | 1 | S:select PFI_CODE from {schema}ENGRDOCS_PFI_CODE PF where PF.ED_DOCTYPE = '{ED_DOCTYPE}'
| ED_DOCTYPE | CHANGE | PFI_CODE_D | 1 | S:select DESCRIPT from {schema}ENGRDOCS_PFI_CODE PF where PF.ED_DOCTYPE = '{ED_DOCTYPE}'
| <Form> | LOAD | RESPOFFICE |  | V:ICAFLUOR
| <Form> | UPDATE | RESPOFFICE |  | V:ICAFLUOR
| <Form> | SELECT | SRD | 1 | S:select SRD from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| SRD | CHANGE | SRD | 1 | S:UPDATE {SCHEMA}DX_2 SET SRD = (SELECT SRD FROM {SCHEMA}REVISION WHERE DOC_RNO = {DOC_RNO} AND REV_ID = {REV_ID}) WHERE DOC_RNO={DOC_RNO}
| <Form> | SELECT | RESDUE | 1 | S:select RESDUE from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| RESDUE | CHANGE | RESDUE | 1 | S:UPDATE {SCHEMA}DX_2 SET RESDUE= (SELECT RESDUE FROM {SCHEMA}REVISION WHERE DOC_RNO = {DOC_RNO} AND REV_ID = {REV_ID}) WHERE DOC_RNO={DOC_RNO}
| <Form> | SELECT | REC_DAT | 1 | S:select REC_DAT from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| REC_DAT | CHANGE | REC_DAT | 1 | S:UPDATE {SCHEMA}DX_2 SET REC_DAT= (SELECT REC_DAT FROM {SCHEMA}REVISION WHERE DOC_RNO = {DOC_RNO} AND REV_ID = {REV_ID}) WHERE DOC_RNO={DOC_RNO}
| <Form> | SELECT | TXML_COM | 1 | S:select TXML_COM from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| TXML_COM | CHANGE | TXML_COM | 1 | S:UPDATE {SCHEMA}DX_2 SET TXML_COM= (SELECT TXML_COM FROM {SCHEMA}REVISION WHERE DOC_RNO = {DOC_RNO} AND REV_ID = {REV_ID}) WHERE DOC_RNO={DOC_RNO}
| <Form> | SELECT | DOCTYPE_D | 1 | S:update {schema}dx_2 set DOCTYPE_D = (select descript from {schema}ENGRDOCS_ED_DOCTYPE dt where dt.ED_DOCTYPE = '{ED_DOCTYPE}' and dt.ED_DOCCAT = '{ED_DOCCAT}') where doc_rno = {doc_rno}
| <Form> | UPDATE | DOCTYPE_D | 1 | S:update {schema}dx_2 set DOCTYPE_D = (select descript from {schema}ENGRDOCS_ED_DOCTYPE dt where dt.ED_DOCTYPE = '{ED_DOCTYPE}' and dt.ED_DOCCAT = '{ED_DOCCAT}') where doc_rno = {doc_rno}
| <Form> | INSERT | DOCTYPE_D | 1 | S:update {schema}dx_2 set DOCTYPE_D = (select descript from {schema}ENGRDOCS_ED_DOCTYPE dt where dt.ED_DOCTYPE = '{ED_DOCTYPE}' and dt.ED_DOCCAT = '{ED_DOCCAT}') where doc_rno = {doc_rno}
| ED_DOCTYPE | CHANGE | DOCTYPE_D | 1 | S:select descript from {schema}ENGRDOCS_ED_DOCTYPE dt where dt.ED_DOCTYPE = '{ED_DOCTYPE}' and dt.ED_DOCCAT = '{ED_DOCCAT}'
| <Form> | SELECT | REC_PEMEX | 1 | S:select REC_PEMEX from {schema}revision where doc_rno = {DOC_RNO} AND REV_ID = {REV_ID}
| REC_PEMEX | CHANGE | REC_PEMEX | 1 | S:UPDATE {SCHEMA}DX_2 SET REC_PEMEX= (SELECT REC_PEMEX FROM {SCHEMA}REVISION WHERE DOC_RNO = {DOC_RNO} AND REV_ID = {REV_ID}) WHERE DOC_RNO={DOC_RNO}
PROJEXEC
| <Form> | INSERT | CA_PRONAME | 1 | S:SELECT CA_PRONAME from {schema}CALOOKUP_CA_PRONAME
| <Form> | UPDATE | CA_PRONAME | 1 | S:SELECT CA_PRONAME from {schema}CALOOKUP_CA_PRONAME
| <Form> | LOAD | CA_PRONAME | 1 | S:SELECT CA_PRONAME from {schema}CALOOKUP_CA_PRONAME
| <Form> | INSERT | CA_CONTRNO | 1 | S:SELECT CA_CONTRNO from {schema}CALOOKUP_CA_CONTRNO
| <Form> | UPDATE | CA_CONTRNO | 1 | S:SELECT CA_CONTRNO from {schema}CALOOKUP_CA_CONTRNO
| <Form> | LOAD | CA_CONTRNO | 1 | S:SELECT CA_CONTRNO from {schema}CALOOKUP_CA_CONTRNO
| <Form> | INSERT | PFI_BUSLINE | 1 | S:SELECT PFI_BUSLINE from {schema}CALOOKUP_PFI_BUSLINE
| <Form> | INSERT | PFI_CLIENT | 1 | S:SELECT PFI_CLIENT from {schema}CALOOKUP_PFI_CLIENT
| <Form> | INSERT | PFI_COSTCENTER | 1 | S:SELECT PFI_COSTCENTER from {schema}CALOOKUP_PFI_COSTCENTER
| <Form> | INSERT | PFI_FACILITY | 1 | S:SELECT PFI_FACILITY from {schema}CALOOKUP_PFI_FACILITY
| <Form> | INSERT | PFI_PROJCITY | 1 | S:SELECT PFI_PROJCITY from {schema}CALOOKUP_PFI_PROJCITY
| <Form> | INSERT | PFI_PROJCTRY | 1 | S:SELECT PFI_PROJCTRY from {schema}CALOOKUP_PFI_PROJCTRY
| <Form> | INSERT | PFI_PROJSTATE | 1 | S:SELECT PFI_PROJSTATE from {schema}CALOOKUP_PFI_PROJSTATE
| <Form> | INSERT | PFI_SBU | 1 | S:SELECT PFI_SBU from {schema}CALOOKUP_PFI_SBU
| <Form> | INSERT | PFI_DISC | 1 | V:100
| <Form> | INSERT | PFI_DISC_D | 1 | V:Project Management
| PFI_CAT | SELECTED | PFI_CAT_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CAT where PFI_CAT = '{PFI_CAT}'
| PFI_CAT | CHANGE | PFI_CAT_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CAT where PFI_CAT = '{PFI_CAT}'
| PFI_CODE | SELECTED | PFI_CODE_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| PFI_CODE | CHANGE | PFI_CODE_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| <Form> | INSERT | PFI_CAT_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CAT where PFI_CAT = '{PFI_CAT}'
| <Form> | SELECT | PFI_CAT_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CAT where PFI_CAT = '{PFI_CAT}'
| <Form> | UPDATE | PFI_CAT_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CAT where PFI_CAT = '{PFI_CAT}'
| <Form> | INSERT | PFI_CODE_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| <Form> | SELECT | PFI_CODE_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| <Form> | UPDATE | PFI_CODE_D | 1 | S:select descript from {schema}PROJEXEC_PFI_CODE where PFI_CODE = '{PFI_CODE}'
| <Form> | INSERT | PE_DOCCAT | 1 | S:select PE_DOCCAT from {schema}projexec_pe_doccat p where p.pe_doctype = '{PE_DOCTYPE}'
| <Form> | UPDATE | PE_DOCCAT | 1 | S:select PE_DOCCAT from {schema}projexec_pe_doccat p where p.pe_doctype = '{PE_DOCTYPE}'
| <Form> | INSERT | PE_FILEIND | 1 | S:select pe_fileind from {schema}projexec_pe_doccat p where p.pe_doctype = '{PE_DOCTYPE}'
| <Form> | UPDATE | PE_FILEIND | 1 | S:select pe_fileind from {schema}projexec_pe_doccat p where p.pe_doctype = '{PE_DOCTYPE}'
| <Form> | INSERT | PE_RETSCHED | 1 | S:select pe_retsched from {schema}projexec_pe_retsched p where p.pe_doctype = '{PE_DOCTYPE}'
| <Form> | UPDATE | PE_RETSCHED | 1 | S:select pe_retsched from {schema}projexec_pe_retsched p where p.pe_doctype = '{PE_DOCTYPE}'
| <Form> | SELECT | PE_DOCCAT_DESC | 1 | S:select descript from {schema}projexec_pe_fileind p where p.pe_fileind = '{PE_FILEIND}'
| PE_DOCTYPE | CHANGE | PE_DOCCAT | 1 | S:select PE_DOCCAT from {schema}projexec_pe_doccat p where p.pe_doctype = '{PE_DOCTYPE}'
| PE_DOCTYPE | CHANGE | PE_FILEIND | 1 | S:select pe_fileind from {schema}projexec_pe_doccat p where p.pe_doctype = '{PE_DOCTYPE}'
| PE_DOCTYPE | CHANGE | PE_DOCCAT_DESC | 1 | S:select descript from {schema}projexec_pe_fileind p where p.pe_doctype = '{PE_DOCTYPE}'
| PE_DOCTYPE | CHANGE | PE_RETSCHED | 1 | S:select pe_retsched from {schema}projexec_pe_retsched p where p.pe_doctype = '{PE_DOCTYPE}'